## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Cloud & DevOps Engineering
INTERN NAME: | Arjun Rathod
PROJECT NAME: | Cal.com Calendar Management Platform on AWS (IP-11803)
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 09-Aug-2026
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Cal.com Calendar Management Platform on AWS |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP-11803
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Mr. Tushar Topale (Cloud Counselage Pvt. Ltd.)
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 02-Aug-2026 | The requirement elicitation revealed that scheduling is completely manual today - no existing scheduling system and no digital tracking of bookings. | Requirements / Discovery | Yes | The client should document the exact team size (20 members) and the meeting platforms used (Zoom, Google Meet) before development begins. | Captured the full background, problem statement, and stakeholder expectations during the first meeting. | Arjun Rathod | Solved | This early clarity helped keep the SRS and design aligned with the client's real workflow.
2 | 03-Aug-2026 | The baseline database backup POC (MongoDB on an EC2 Ubuntu Server with a single Bash script that automatically takes a backup and converts it to ZIP) was identified as a reusable automation framework for the project. | Technical / Automation | Yes | Reuse and extend the verified backup framework rather than building new automation from scratch. | Kept the MongoDB backup script on the EC2 Ubuntu Server running (backups saved on local storage, S3 migration possible later) and used the same automation-first mindset for AWS deployment. | Arjun Rathod | Solved | Demonstrated the automation-first approach expected in the internship deliverables.
3 | 04-Aug-2026 | A very tight one-week timeline was identified as the biggest risk to project delivery. | Project Management / Planning | Yes | Adopt a phased milestone plan with daily tracking and early stakeholder alignment. | Created the Project Charter, RAID Log, and WBS; set clear milestones for each phase of the week. | Harshada Topale | Solved | The phased plan kept the team on schedule and made progress easy to review.
4 | 06-Aug-2026 | During local development, container connectivity issues were expected because the multi-container docker-compose stack had many moving parts. | Technical / Development | Yes | Use .env files and docker-compose to emulate the deployment locally before touching AWS. | Created the .env files and docker-compose.yml stack and verified that all containers could communicate locally. | Arjun Rathod | Solved | Local emulation saved significant time by catching configuration mistakes before cloud deployment.
5 | 07-Aug-2026 | Cost was a major constraint; running baseline EC2 instances would waste budget for a small team. | Cost Management / Architecture | Yes | Use serverless AWS Fargate instead of EC2 to eliminate baseline management costs, and add auto-scaling. | Deployed Cal.com on AWS ECS with Fargate and configured auto-scaling (scale-up > 70% CPU for 3 min, scale-down < 30% CPU for 10 min). | Arjun Rathod | Solved | The serverless design kept the solution cost-effective while remaining scalable for the 20-member team.
6 | 08-Aug-2026 | Monitoring and logging needed to be set up so that the platform health is visible centrally. | Operations / Monitoring | No | Set up CloudWatch Logs (/ecs/calcom-app) for centralized logging and CloudWatch for metric visibility. | Configured CloudWatch Logs for the ECS service and simulated the scaling rules and logging to verify they worked. | Arjun Rathod | Solved | Simulation of scale rules and log checks passed, confirming the monitoring setup before handover.
7 | 09-Aug-2026 | A recurring issue in such projects is incomplete or inconsistent documentation at handover. | Documentation / Closure | Yes | Prepare all deliverables (charter, SRS, WBS, design spec, report, lessons learnt) consistently before closure. | Compiled and reviewed all deliverables for final handover, keeping data consistent across documents. | Harshada Topale | Solved | The document set is aligned and ready for final submission.