## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Cal.com Calendar Management Platform for Cloud Counselage Pvt. Ltd.
PROJECT SPONSOR | Mr. Tushar Topale (Founder, Cloud Counselage Pvt. Ltd.)
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 02-Aug-2026 (MM-DD-YYYY: 08-02-2026)
EXPECTED COMPLETION DATE | 09-Aug-2026 (MM-DD-YYYY: 08-09-2026)
ESTIMATED COST | N.A. (Internship project executed on open-source tools and AWS cloud; costs limited to AWS usage on free-tier/credits)
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To deploy a centralized, secure, and automated calendar management platform for the client using the open-source Cal.com tool on AWS cloud infrastructure, enabling efficient scheduling across multiple platforms (Zoom, Google Meet) for the client and his team of 20 members, while automating booking workflows and securing company data.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | The client manages an extremely busy schedule with back-to-back meetings across multiple platforms (Zoom, Google Meet, etc.), which makes calendar management and tracking highly inefficient for him and his team of 20 members. Manual scheduling consumes valuable time, creates booking conflicts, and increases the risk of missed meetings and double bookings. Deploying Cal.com - a powerful open-source calendar management tool - centralizes scheduling, automates booking workflows, and secures company data. By migrating the verified framework to AWS, the solution becomes highly scalable and cost-effective, eliminating upfront license costs while providing enterprise-grade reliability. As a baseline proof-of-concept, an automated database backup was built and demonstrated. On an EC2 Ubuntu server, MongoDB was installed and some temporary users were added for testing. A single Bash script was written that automatically takes a backup of the MongoDB data and converts it into a ZIP file. Right now the backup is saved on the local storage of the server, and the same script can be upgraded later to shift the backups to Amazon S3 cloud storage.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | GOALS: 1. Successfully deploy Cal.com on AWS ECS (Fargate) within the project timeline. 2. Centralize calendar management for the client and his 20-member team. 3. Automate booking workflows with Zoom and Google Meet integrations. 4. Achieve cost-efficient scaling - add a task when average CPU > 70% (3 consecutive minutes) and terminate idle tasks when average CPU < 30% (10 consecutive minutes). 5. Secure user data via AWS RDS PostgreSQL and HTTPS via AWS Certificate Manager, with centralized monitoring through AWS CloudWatch. METRICS: - 100% deployment completed within 02-Aug-2026 to 09-Aug-2026. - Automated MongoDB backup working on EC2 Ubuntu Server - one Bash script takes the backup and converts it into a ZIP file saved on local storage (can be shifted to S3 later). - Auto-scaling and CloudWatch logging verified (scale simulation passed). - All 20 team members able to book schedules through the platform.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | - Project Charter - Requirement Elicitation Questionnaire - Software Requirement Specifications (SRS) - Work Breakdown Structure (WBS) - Software Design Specification - Project Report - Lessons Learnt Log
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | - Deployment of Cal.com open-source calendar management platform on AWS. - Compute and orchestration using AWS ECS (Elastic Container Service) with AWS Fargate (serverless containers). - Fully managed data storage using AWS RDS PostgreSQL. - Traffic routing and SSL (HTTPS) via AWS Application Load Balancer (ALB) with AWS Certificate Manager (ACM). - Fully automated CI/CD using GitHub Actions (.github/workflows/deploy.yml) - push to main branch builds the Docker image, pushes to Amazon ECR, and updates ECS tasks. - Auto-scaling policy for the 20-member team (scale-up/down based on CPU utilization). - Centralized monitoring and logging via AWS CloudWatch (CloudWatch Logs - /ecs/calcom-app). - Local development and verification using .env files and multi-container docker-compose.yml. - Baseline automated MongoDB backup POC - on EC2 Ubuntu Server, MongoDB with temporary test users, and a single Bash script that takes an automatic backup and converts it into a ZIP file stored locally.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | - Mobile application development for Cal.com. - Integrations beyond Zoom and Google Meet (e.g., Microsoft Teams, Skype) in this phase. - Custom feature development or modification of Cal.com source code. - Multi-region deployment and disaster recovery setup. - 24x7 on-call production support after handover. - Payment or billing gateway integrations.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | - Harshada Topale - Project Manager - Arjun Rathod - Cloud & DevOps Engineer (Intern) - built and delivered the project - Cloud Counselage Pvt. Ltd. mentorship and review support (Project built and delivered by a single intern member - Arjun Rathod, under PM guidance)
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | - AWS Cloud account and services (ECS, Fargate, RDS, ALB, ACM, CloudWatch, ECR, EC2). - GitHub repository with GitHub Actions for CI/CD. - Docker and Docker Compose for local containerization. - Cal.com open-source documentation and community. - EC2 Ubuntu Server with MongoDB installed (for the backup POC). - Development workstation, internet connectivity, and monitoring access.
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | - AWS Fargate: pay-per-use serverless container compute (minimal for a 20-member team). - AWS RDS PostgreSQL: managed database instance (free-tier eligible initially). - AWS ALB: per-hour plus LCU-based charges. - Cal.com and all tooling are open-source - zero licensing cost. - Overall project cost kept within internship budget using AWS free-tier and credits (no paid manpower).
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Mr. Tushar Topale (Founder, Cloud Counselage Pvt. Ltd.)
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | - Mr. Tushar Topale - Sponsor and Process Owner - Mr. John Doe - Target Business Owner / End Customer - Harshada Topale - Project Manager - Arjun Rathod - Cloud & DevOps Engineer - Cloud Counselage Pvt. Ltd. - Supervising organization - 20-member team - End users of the platform
END CUSTOMER (Mention the client name.) | Mr. John Doe (Target Business Owner) and his team of 20 members
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. AWS credential / service limit issues causing deployment delays - Mitigation: early environment setup and configuration review. 2. ECS / Fargate misconfiguration leading to service downtime - Mitigation: local emulation with docker-compose before cloud deployment. 3. Database connectivity failure between Cal.com and RDS PostgreSQL - Mitigation: security group testing and connection verification. 4. Auto-scaling misconfiguration increasing AWS billing - Mitigation: strict scaling policy (70%/30% thresholds) and testing. 5. CI/CD pipeline failure during build or ECR push - Mitigation: validate deploy.yml and Docker image locally. 6. Zoom / Google Meet API limitations for integration - Mitigation: rely on Cal.com native integrations. 7. Very tight one-week timeline - Mitigation: phased milestones and daily tracking.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | - AWS Free Tier / internship credits are available for the project. - GitHub Actions, Docker, and Docker Compose are available without additional cost. - Cal.com open-source license permits commercial deployment. - The team has basic AWS and Linux knowledge and reliable internet access. - The MongoDB backup script on the EC2 Ubuntu Server keeps working and saving backups on local storage. - The client will provide access to scheduling accounts (Zoom, Google Meet) for integration testing.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | - Strict timeline of one week (02-Aug-2026 to 09-Aug-2026). - AWS billing must be minimized (cost-effective design only). - Availability limited to the selected AWS region. - Company data must remain secure (encryption, HTTPS, restricted access). - No custom modifications to Cal.com core source code. - Deliverables required in standard formats (XLSX, DOCX, PPTX).
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | Completion Date: 08-03-2026 Requirement gathering is marked as complete after submission of the SRS document. Stakeholder interviews and alignment were done with the sponsor and end customer.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | Completion Date: 08-05-2026 Planning phase is considered complete after a duly completed Work Breakdown Structure (WBS), Project Schedule, and RAID logs.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 08-06-2026 Design stage is considered complete after submission of the Software Design Specification and architecture/wireframe files.
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 08-07-2026 Development stage is considered complete after local emulation - .env files, multi-container docker-compose.yml stack, and verified container connectivity.
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | Completion Date: 08-08-2026 Testing stage is considered complete after submission of Test Reports (scale-rule simulation and CloudWatch logging verified).
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | Completion Date: 08-09-2026 Deployment stage is considered complete after the automated CI/CD pipeline (GitHub Actions -> ECR -> ECS) successfully deploys the application on AWS.
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | Completion Date: 08-09-2026 Project closure is considered complete after handover of the Lessons Learnt Log, Project Report, and installation guide.